This document includes data that may not be disclosed outside of the intended recipient and may not be duplicated, used, or disclosed, in whole or in part, for any other purpose.

AIS Use Only:FFP-v11/24; pss_opportunityid

Date: Enter SOW Date

Prepared for

Customeridname

Contract/Technical Point of Contact

Enter Client POC Name, Enter Client POC Title

Enter Email address

Enter Phone number

Prepared by

Applied Information Sciences, Inc.

Contracts Point of Contact

Rebecca Carter, Contracts Manager

rebecca.carter@ais.com

443-393-3548

Statement of Work

name

Table of Contents

1.	Introduction	1

1.1	Background and Objectives	1

2.	Scope of Engagement	1

2.1	In Scope	1

2.2	Out of Scope	1

2.3	Tech Assumptions	1

3.	Approach and Project Management	2

3.1	Visual Timeline	2

3.2	Project Management	3

4.	Project Execution Phase Details	4

4.1	Project Initiation  	4

4.1.1	Project Onboarding/Prerequisites	4

4.1.2	Project Kickoff	4

4.2	Project Execution Phase Name	5

4.3	Project Closeout	6

5.	Summary of AIS Deliverables	6

6.	Client Requirements	6

7.	Assumptions and Dependencies	7

8.	Place of Performance	8

9.	Performance Period	8

10.	Price Proposal	9

10.1	Price Summary	9

10.2	Payment Schedule and Invoicing	9

10.3	Travel	10

11.	Administrative	10

11.1	Client Points of Contact (POCs)	10

11.2	Deliverables Acceptance Procedure	10

11.3	Delays	11

11.4	Project Change Control Procedure	11

11.4.1	Reduction in Scope	12

11.4.2	Increase in Scope	12

11.5	Escalation Procedure	12

11.6	Stop Work Order	13

11.7	Termination for Convenience	13

11.8	Warranty	14

12.	Validity of SOW	14

13.	Closing	15

# Introduction

This Statement of Work (SOW) by and between Customeridname (Client) and Applied Information Sciences, Inc. (AIS) applies to and governs the following engagement: name. This SOW forms a part of, and is subject to, the terms and conditions of the Master Services Agreement (MSA), dated Enter MSA Date, between AIS and Client. All services provided under this SOW constitute “Services” for purposes of the MSA. All capitalized terms not defined herein shall have the meaning set forth in the MSA. Should the terms listed in this SOW be different from those listed in the MSA the terms of this SOW shall supersede those of the MSA.

## Background and Objectives

Add some background information, such as a description of the background behind this project, why this project is being done, and for what purpose and business goals; include the project goal and a bulleted, detailed and clear listing of the project objectives. NOTE do NOT include technical scope in this section. This is the WHY section of the SOW.

Customeridname has defined the set of business objectives as follows:

Objective 1

Objective 2…

# Scope of Engagement

## In Scope

Describe the detailed technical scope of the work we will be performing This section is where we will describe the WHAT we will be doing as detailed as possible (i.e. AIS will migrate 5 servers or we will develop 10 canvas apps) and the how we will do it is in the subsections below.

During the course of this engagement, AIS will…

## Out of Scope

Unless otherwise expressly stated, AIS will not be responsible for the following aspects of this project; Client will assume responsible for performance of the tasks that are applicable to the project in a time frame that will ensure that there are no negative impacts to project progression or deliverables.

- Insert out of scope items.

## Tech Assumptions

Please add general assumptions for the type of project you are performing and additional project specific assumptions. Note this section is for technical assumptions be sure to include any prerequisites required before kickoff.

The sections below provide a detailed description of the work which will be performed under this SOW. In developing this SOW AIS has made the following technical assumptions. General project assumptions and dependencies are listed in a separate section of the SOW.

# Approach and Project Management

This is the HOW section. This section is used to describe the project phases, tracks, or workstreams. For each project, AIS usually starts with Project Management and Planning and ends with Closeout. Add other necessary phases/tracks/workstreams in between.

Add a bulleted list of the phases, tracks, workstreams, etc. to provide Client with an understanding of how the project is being structured. Provide any additional information that helps define these phases, tracks, workstreams, etc., such as a short summary of the workstreams or tracks that make up each phase.

Use the structure of this section to detail the engagement, describing activities that take place within each phase, track, or workstream. Remove any sections that you may not need.

To meet the identified business objectives, AIS proposes the following project (task areas, phases, tracks, workstreams):

- Project Initiation

- Project Execution Phases….

- Closeout

Tools

Please see the sections below, please use the section as appropriate for your effort. Remove any tools which may not be relevant to your engagement and add as appropriate. Please make note if the client is required to provide the tool or pay for the license, otherwise it will be assumed that these tools are AIS owned and paid for.

During the course of this engagement AIS may utilize the following third-party tools.

Security and/or Infrastructure work:

| - Azure Active Directory Premium (2, Conditional Access) - Exchange Online - Insider Risk Manager - Managed Security Services | - Microsoft Defender (Endpoint, Cloud Apps, Identity, Office) - Microsoft Information Protection (MIP) - Microsoft Cloud App Security (MCAS) - Microsoft Intune |
| --- | --- |

Modern Work:

| - Microsoft 365 Apps - Outlook Mobile - SharePoint Online | - Teams (Apps, Frontline Workers, Meetings, Phone Enabled Users, Platform, Rooms) - Viva (Connections, Engage, Goals, Insights, Learning, Topics) |
| --- | --- |

Business Apps:

| - Dynamics 365 (Additional Database Storage (Qualified Offer) - Customer Engagement Plan - Customer Service Enterprise (Customer Voice USL, Finance, Operations, Sales Enterprise Edition, Team Members) - Microsoft Copilot Studio (User License) - Microsoft Dynamics CRM Online | - Microsoft Relationship Sales Solution - Power Apps Premium - Power Automate (Hosted RPA, Per Flow Plan, Per User Plan, Premium, Process, Unattended RPA Add-On) - Power BI |
| --- | --- |

## Visual Timeline

Describe the timeline by providing details pertaining to the phases, tracks, workstreams, etc. described above. Include a graphic (with caption) showing the timeline, dates, weeks of occurrence, and duration of each phase, track, workstream, etc.

Be sure to show the kickoff meeting 5 to 10 days after the period of performance (POP) start date. Below is a sample timeline graphic.

AIS will follow the project timeline set forth in the graphic below.

Figure 1 - Project Timeline

## Project Management

Contracts has reviewed and approved this section. Please turn on Review > Track Changes to help Contracts further review, if you update this section.

Project Management is a key part of every project AIS performs. Project Management helps AIS meet our clients’ needs by standardizing routine tasks to optimize project delivery. It ensures that available resources are used in the most effective and efficient manner and provides organizational leadership and other stakeholders with insight into the project performance and execution. AIS places paramount importance on the overall communication and leadership of the project to ensure a successful completion.

Key Activities & Effort

The Project Management function is multifaceted and includes:

- Daily monitoring for overall project progress

- Communication to stakeholders

- Managing resources across project activities

- Managing the project budget

- Coordinating project interdependencies

- Managing project documentation

- Managing risk and taking corrective action when necessary

Project Management Deliverables

Only include Monthly Status Reports, if required

Throughout the engagement, AIS will provide the following Project Management deliverables:

| Deliverable | Summary | Due |
| --- | --- | --- |
| Weekly Status Reports | MS Word document listing key project activities completed that week, planned activities for next week, key project risks and mitigation strategies, and any project issues. | Weekly (Friday) |

# Project Execution Phase Details

## Project Initiation

This should be the first phase of every SOW, below is a sample Project Initiation Phase description that illustrates formatting and expected structure.

During the Project Initiation Phase, AIS will finalize its personnel assignments, complete team member onboarding, and ramp up to productivity. AIS will meet with client business and technical stakeholders to ensure a mutual understanding and alignment of business goals, objectives, and high-level requirements, to voice concerns, identify potential issues, share ideas, and discuss the project plan and approach. Client will work with AIS to ensure all required system access is provided prior to the start of Project Execution.

Key Activities & Effort

Include a description of the activities occurring during this phase, track, workstream, etc.  Sample of Planning activities is provided below. This Key Activities & Efforts section may be further broken-down using Heading 4 to show multiple subsets of activities occurring in the phase, track, workstream, etc.

### Project Onboarding/Prerequisites

Examples:

- Client will provide AIS with access to required equipment

- Access to necessary systems

- Approval of resources if required

- Documentation of procedures for bringing on new resources.

### Project Kickoff

AIS will conduct a project initiation or kickoff meeting with client stakeholders at the end of the Project Initiation Phase, between 5 and 10 business days after the start of the period of performance of this SOW to define the approach for successfully completing this engagement. During the initiation meeting, attendees will review and establish the required process startup for working sessions, proposed meeting cadence, and team formation for AIS and client stakeholders for these meetings and this engagement.

Project Initiation and Project Planning will include the following items:

- Schedule and proceed with kickoff meeting and presentation

- Form team

- Identify document and agree on project stakeholders, these will be the points of contact for…..

- Establish process startup and meeting cadence

- Discuss methods of access and collaboration for work sessions

- Identify Client Provision and Dependencies and timeline if required

Client Provisions

Include a bulleted list of deliverables Client will provide during the described phase, track, workstream, etc., as well as a schedule setting forth in detail when Client is obligated to provide the deliverable. It is important to specify these client deliverables and the schedule, as delays may impact our ability to deliver our contractual obligation.

Described below are the specific client provisions required to complete the Project Initiation phase

- Client deliverable 1…

Project Initiation Deliverables

Include all AIS contractual deliverables. These deliverables must: 1) be tangible and can be approved through a deliverable acceptance form 2) correspond to those listed in the Payment Schedule and Invoicing Section.

Listed below are the AIS deliverables for the Project Initiation phase.

| Deliverable | Summary | Due |
| --- | --- | --- |
| Project Initiation Meeting Briefing | Coordination of meeting and delivery of Power Point presentation describing project execution strategy. | No later than 10 days from start of period of performance |

- v

## Project Execution Phase Name

Use the structure from 4.1 to add each of the additional Project Execution Phases, this is the implementation of the project (one section per phase/task area needed for the execution of the project) and include the Key Activities and Effort and Deliverables sections.

Discovery and Design (include time box lang) (scope ends up being larger than we assume we need to take a step back and modify the SOW)

Implementation and UAT (if we don’t include UAT we need an assumption that this is out of scope)

Go Live Training and knowledge transfer (if the client elects to not go live at the end of the project we need another SOW to cover go live support)

Example blank section

Next, AIS will …

Key Activities & Effort

Include description of activities…

- Activity 1…

- Activity 2…

Client Provisions

Described below are the specific client provisions required to complete the Project Execution Phase Name phase

- Client deliverable 1…

Project Execution Phase Name Deliverables

Listed below are the AIS deliverables for the Project Execution Phase Name phase.

| Deliverable | Summary | Due |
| --- | --- | --- |
| Deliverable | Summary | date |

## Project Closeout

This should be the last phase of the project.

AIS will provide a project closeout meeting to discuss the overall project and review challenges, successes, difficulties, and observations for future learnings.

Client Provisions

Described below are the specific client provisions required to complete Project Closeout

- Final acceptance of the project.

Project Closeout Deliverables

Listed below are the AIS deliverables for the Project Closeout Phase.

| Deliverable | Summary | Due |
| --- | --- | --- |
| Project Closeout Report | MS word document that lists the status of each deliverable and the sign off of each. | No later than 5 days prior to the end of the period of performance. |

# Client Requirements

Below are specific requirements that the Client must address/provide during project execution in addition to any Client provisions identified above. Failure to address provisions or requirements in a timely manner may result in project delays and/or adjustments to project scope/cost in accordance with the Delays Section and the Project Change Control Section:

Client will designate a primary point of contact listed in the Client POC Section who shall be empowered to act for Client and make binding decisions.

Client’s staff will be available for meetings with a moderate amount of advance notice (a few days). In some situations, certain key members of Client’s team may need to be available with little notice to clarify points and answer questions either on-site at the Client’s facilities, by telephone, and/or by email. AIS will document any inability of Client staff availability that leads to a delay in AIS’s performance and provide Client written notice of the same.

Client will provide timely responses to questions, meeting requests, system reviews, and system acceptance. Delays in responding to such requests could impact the project cost and AIS’s ability to adhere to the project timeline.

Client will provide access to necessary resources (e.g., Subject Matter Experts (SMEs), network access, etc.) will be provided upon project kick-off and for the duration of the project. Any significant delay in providing access to these necessary resources could impact the project, including the project cost and timeline.

Client will purchase all software licenses required for Client’s hardware, including test, development, and production machine(s).

For Microsoft reporting to ensure AIS can get as-needed technical resources and support from Microsoft on this project, the Client will add AIS’ Partner Admin Link (PAL) ID 51094 to their Azure subscriptions, affiliating AIS as a Microsoft Partner for the scope of this statement of work (SOW). Microsoft PAL reporting uses the existing link between the client’s Azure Subscription and their Microsoft account and will not alter any aspects of the Azure subscription or access rights. For select Microsoft services, customer may also support AIS in Claiming Partner of Record (CPOR) as the method for affiliation.

# Assumptions and Dependencies

Contracts and attorneys have reviewed and approved this section. Please turn on Review > Track Changes to help Contracts further review, if you update this section.

The sections above provide a detailed view of the scope of work covered by this SOW. In an effort to provide a clear understanding of what is not included within the AIS scope of work under this SOW, and to clarify underlying assumptions and dependencies that the work under this SOW depends upon, AIS has listed in this section assumptions and dependencies to which the Parties have agreed. These assumptions and dependencies are in addition to any other assumptions, dependencies, constraints, conditions, and terms specified elsewhere in this SOW.

AIS resources need to be onboarded and project pre-requisites need to be met by project kickoff or XXXX date or project cannot move forward.

AIS will provide Client written notice of any delay(s) that may impact AIS’ performance. AIS will not be liable for any failure to perform in accordance with the project timeline caused solely by any such delay by Client or circumstances outside of our control if AIS provides such notification. Client understands that excessive delays that are caused solely by Client may result in an increase in cost. AIS will inform Client prior to reaching this point and work with Client to issue a change order to adjust the cost and timeline accordingly.

AIS will make itself available for on-site meetings and work when determined beneficial; however, other than such Client-requested on-site meetings and work, AIS will perform its work at AIS-designated (not Client) facilities.

The price provided is based on the described scope and estimated period of performance as outlined in this SOW, any change in scope, any change in the number of weeks work will be performed, or changes to both will require a change request and an adjustment to price.

If a change order is issued to extend this work, then such change order must be fully executed prior to the end date of this SOW in order for work to continue without a break in service, unless written authorization is provided.

# Assumptions regarding AI Outputs

AIS does not guarantee the accuracy, completeness, or reliability of the generated content. Users should exercise their own discretion and judgment when interpreting and using the information provided by the AI model. An integrator of OpenAI, AIS does not assume any liability for misuse of the of application by the Clients. AIS is not responsible or liable for the output produced by the application and is not responsible or liable for the actions resulting from use of the output. These assumptions help set realistic expectations and clarify the responsibilities of both parties regarding the use and outcomes of the AI system.

- Performance Assumption: The AI’s performance is based on the quality and quantity of the data it was trained on, and its output is probabilistic in nature.

- Data Quality Assumption: The accuracy of the AI’s output is contingent upon the quality, completeness, and relevance of the input data provided by the client.

- Use Case Assumption: The AI is designed for specific scenarios, and its performance may vary if applied to contexts outside of its intended scope.

- Continuous Learning Assumption: AI may improve over time as it processes more data, and its outputs may change as a result of this continuous learning process.

- Third-Party Dependencies Assumption: The AI’s outputs may be influenced by third party tools or platforms it interacts with, and any changes to these external systems could affect the AI’s performance.

These limitations may potentially impact the project outcomes.

# Place of Performance

See the below location options, these are the most common work locations, please adjust as necessary to fit where work will be done for this SOW (either removing the non-applicable choice or adding to the list of your situation is not covered), we need to make sure we accurately list who will be performing work on this SOW and where the work will be performed in order to be compliant with MSAs and other agreements. We may also need to list out what type of data or systems each location will have access to, this is currently not part of the template and will need to be added on a case-by-case basis.

AIS may perform work related to this SOW:

- On-site at Client facilities by US based AIS employees and approved subcontractors

- Both remotely and on-site at AIS facilities by US based employees and approved subcontractors

- By employees of AIS’ wholly owned subsidiary, Applied Info Services, located in Hyderabad, India

- Remotely by non-US based AIS employee and approved subcontractors

# Performance Period

AIS anticipates an overall period of performance of XX consecutive weeks, with an expected start date of Enter SOW Start Date and for work to continue through Enter SOW End Date. Below please find a breakdown of the period of performance by project initiation, execution and closeout. Should the start date be delayed by mutual agreement of both Parties, the end date will shift to compensate for the delayed start date.

- Project Initiation Phase (project onboarding): Start date – (give at least on to two week time frame this should end with project kickoff)

- Project Execution Phases: Starts after Project Initiation – Final Delivery submission)

- Project Close Out Phases: (enter a time frame large enough to cover the close out meeting and the final deliverable acceptance period)

# Price Proposal

## Price Summary

The work for this project is being performed under a fixed-price deliverable/milestone or a monthly fixed-fee arrangement.

The amount to be billed under this SOW is detailed in the Payment Schedule and Invoicing section below. In no event shall Client be invoiced or obligated to pay any amount in excess of the total fixed fee set forth below, unless such amount is approved by Client via a project Change Order.

AIS shall invoice Client upon receipt of Client’s acceptance per the Deliverable Acceptance Procedure section below. Payment terms are as specified in the MSA between Client and AIS.

## Payment Schedule and Invoicing

Use the chart below to include all your deliverables listed in the Scope of Engagement section above. Specify the associated cost, with Task Area showing the associated phase / milestone, please note if you are using Phases or Milestones in the SOW update the term Task Area to the proper term for this SOW. Project Close Out Phase must be set up as a separate deliverable that way if changes or early termination happens, we can easily charge for the close out.

Detailed below is the invoice schedule to include major milestones and project deliverables. This schedule assumes a project start date of XXXXXX.

| Inv. # | Invoice Date | Deliverables & Work Products | Amount | Running Total |
| --- | --- | --- | --- | --- |
| example: 1 | 1/1/2023 | Milestone/Project Phase Name: - Deliverable | $10,000.00 | $10,000.00 |
| Grand Total (excluding any and all applicable taxes): |  |  |  |  |

**For Firm Fixed Priced SoWs where the contract amount is divided into monthly payments, Client understands that the monthly amount is not necessarily reflective of the actual milestones completed during said month. If the scope of work is decreased or the SOW terminated, then Client understands an adjustment fee will be charged to cover the scope of work actually completed.

## Travel

AIS [does/does not] expect to travel during the course of this project. Should these expectations change, and travel is required, AIS shall obtain approval of all travel in advance in writing by Client.

Meals and incidentals will be invoiced based on U.S. Government per diem rates (available at http://www.gsa.gov/portal/content/104877). Travel (air or rail), rental car, and lodging will be reimbursed based on actual costs.

# Administrative

## Client Points of Contact (POCs)

Client POCs for this project are listed below.

Invoicing POC: Client shall provide information regarding the point of contract AIS shall submit our invoices to. Unless otherwise agreed to all invoices will be sent out via email.

Primary POC: Client shall designate one individual as the Client Primary POC under this SOW. This point of contact shall be the technical POC for this project and shall be responsible for receiving and accepting deliverables.

|  | Invoicing POC | Primary POC |
| --- | --- | --- |
| Name |  |  |
| Title |  |  |
| Mailing Address |  |  |
| Email Address |  |  |
| Phone Number |  |  |

## Deliverables Acceptance Procedure

Contracts and attorneys have reviewed and approved this section. Please turn on Review > Track Changes to help Contracts further review, if you update this section.

Client will review and accept AIS Deliverables according to the following procedure:

- Within five (5) business days of receipt of each project Deliverable, the Client’s Primary POC will either accept such Deliverable or provide AIS with a written list of requested revisions to conform the Deliverable to this SOW. If AIS receives no response from the Client’s Primary POC within five (5) business days, then the Deliverable will be deemed accepted and complete.

- If AIS receives feedback on submitted deliverables, then AIS will incorporate any revisions requested by Client to conform the Deliverable to this SOW within thirty (30) days of receipt of the request or within a mutually agreed upon timeline and resubmit the deliverable for approval.

- Revisions requested by Client that are not within the scope of this SOW will be managed in accordance with the Project Change Control Procedure below.

- Any conflict arising from the Deliverables Acceptance Procedure will be addressed as specified in the Escalation Procedure below.

## Delays

AIS shall provide Client with written notice of any delay(s) that may impact AIS’ performance on this project and address those delays per this section. Additionally, AIS shall inform client when it becomes aware of any potential delays and work with Client to address those potential delays prior to them becoming actual delays or impacting project delivery.  Status reports or email notification informing Client of potential or actual delays will be considered official notification. Client understands that AIS will continue to charge for time during delays caused by client which will result in additional funding being required to cover the time delay and project deliverables.

AIS will be liable for any increase in cost for delays that are solely due to our responsibility or actions. AIS will not be liable for any failure to perform in accordance with the project timeline caused by delays which are outside of AIS’ control, including but not limited to those caused either by Client, a third party working with Client, or by any other reason outside of AIS’ control. AIS will inform Client of the delays and the impact those delays are having on the project and work with Client on a remediation plan. If a change order is required to adjust project scope, funding, or timeline AIS will issue a Change Order in accordance with the Project Change Control Procedures.

Depending on client the paragraph below may be removed:

Client understands that system access is critical to being able to complete work required under this SOW and any delay in obtaining access to Client systems, environments, or resources will result in an increased cost of XX/per week for the first two weeks of delay. Should the delay last longer than two weeks, then AIS shall work with client on a contract modification to adjust the contract price and schedule in accordance with the Project Change Control Procedures. This increased cost shall be applicable to any delay in obtaining access to Client systems, environments or resources as defined in the Client Provision above.

## Project Change Control Procedure

The following process will be followed if a change to this SOW is required.

- A SOW Modification or Change Order will be issued to make any changes to the scope of work set forth in this SOW, the period of performance, the pricing, or staffing. The Modification or Change Order will describe the requested change and the effect the change will have on the project. Any Change Order will be issued within the same contract type that was originally awarded under this SOW. Any request to modify the contract type is subject to approval and may result in an additional fee and/or a new SOW to be issued.

- A Modification or Change Order must be signed by authorized representatives from both Parties to authorize implementation of any change to the scope of work, period of performance, pricing or other provision in this SOW. Until a change is agreed to in writing, both Parties will continue to act in accordance with the latest agreed version of the SOW.

### Reduction in Scope

Any change order resulting in a reduction of scope may also affect the overall cost or period of performance for the project.

For Deliverable or Milestone based projects Client understands that the pricing associated with each deliverable/milestone covers both the cost of the deliverable/milestone and additional project costs which are spread-out over the entire project. A reduction in scope will result in a reduction of a portion of the effected deliverable/milestone. If work has already begun on the affected deliverable/milestone, AIS shall receive a pro-rated payment for the portion of work already performed.

For projects where the work is being invoiced on a monthly Fixed Fee basis, Client understands that the monthly amount is not necessarily reflective of the actual milestones completed during said month. If the scope of work is reduced Client understands that an adjustment fee will be charged to cover the scope of work actually completed prior to the change order but that was not covered by the fees invoiced.

### Increase in Scope

Any change order resulting in an increase in scope may also affect the overall cost or period of performance for the project.

For Deliverable/Milestone based projects depending on the changes requested AIS will either increase the cost of existing deliverables/milestones or add new deliverables/milestones and their corresponding price to the project. Adjustments to the overall project timeline may also be required.

## Escalation Procedure

Contracts and attorneys have reviewed and approved this section. Please turn on Review > Track Changes to help Contracts further review, if you update this section.

The following procedure will be followed if resolution is required of a conflict arising during the performance of this SOW. During Project Kickoff, the AIS and Client POCs required for these Escalation Procedure will be identified.

- When a conflict arises between Client and AIS, the project team member(s) will first strive to work out the problem internally.

- Level 1: If the project team cannot resolve the conflict within two (2) working days, the Client Primary POC and AIS Project Manager will meet to resolve the issue.

- Level 2: If the conflict is not resolved within three (3) working days after being escalated to Level 1, the Client Executive Sponsor will meet with the AIS Executive Sponsor to resolve the issue.

- If the conflict is resolved by either Level 1 or Level 2 intervention, any changes to this SOW arising from the resolution will be documented as a Change Order to this SOW and signed by both Parties.

- If the conflict remains unresolved after Level 2 intervention, then the Parties may exercise their respective rights under the MSA.

During any conflict resolution, AIS agrees to otherwise continue performance under this SOW relating to work not in dispute, to the extent practicable pending resolution of the conflict. Client agrees to pay invoices for Services that are not in dispute under the SOW and the MSA, in accordance with the terms of the MSA.

## Stop Work Order

The Client may, at any time, by written order to AIS, require AIS to stop all, or any part, of the work under this SOW for a period of time, not to exceed thirty (30) calendar days. The written notice shall specifically identify the start date of the Stop Work Order and the scope of the work effected by the Stop Work Order. Any work performed after the start date of the Stop Work Order will not be paid. Client will pay AIS for any work performed up to the start date of the Stop Work Order. For Firm Fixed Prices projects, including Deliverable and Milestone Projects, Client will pay a pro-rated amount for the work already performed as of the effective date of the Stop Work Order, the remaining portion will be invoiced once the Stop Work Order is lifted and work resumes. For Time and Materials projects, Client will pay for the hours worked up until the start date of the stop work order.

AIS will not restart work until a written notice from Client to lift the Stop Work Order is received. AIS will resume work within thirty (30) calendar days, or within a mutually agreed upon time frame, from receipt of the notice to lift the Stop Work Order. For Stop Work Orders seven (7) calendar days or less AIS will hold the resources who are actively working on the project at the start of the Stop Work Order. Unless AIS is notified at the start of the Stop Work Order that the Stop Work Order is expected to be longer than seven (7) days and there is no need to hold the resources, then after the first seven (7) days of the Stop Work Order AIS shall invoice Client for a fee of 50% of the average weekly cost for those resources. Client understands that if the period of Stop Work is longer than seven (7) calendar days AIS’ resources may be reassigned to another project and there is no guarantee the same resources will be available once the Stop Work Order is lifted.

If the period of Stop Work extends beyond thirty (30) calendar days AIS has the right to terminate this agreement upon written notice without penalty.

Any impact to time or costs caused by the Stop Work Order, regardless of the duration of the Stop Work Order, will be the responsibility of the Client and AIS will issue a Contract Modification per the Project Change Control Procedures of this SOW which will need to be executed prior to AIS re-starting work.

## Termination for Convenience

Please see the termination for convenience options this is for projects which we wish to alter the termination for convenience clauses already listed in the MSA. Please NOTE not all options are suitable and those which do NOT apply should be removed from the SOW.

Standard Statement:

Should the Client want to terminate this SOW early for convenience for any reason they must provide written notice to AIS at least 30 days prior to the date of termination. Client shall pay for any work performed by AIS prior to the date of termination. For deliverable/milestone projects client shall pay for a pro-rated portion of the deliverables/milestones AIS has performed services on up to the date of termination.

Client understands that for SOWs terminated early, AIS and Client will still perform the SOW Close Out Phase to wrap up the Statement of Work and invoice for the close out phase.

Managed Services/ Auto Renewals/ Or prepaid support

Should the Client want to terminate this SOW early for convenience for any reason they must provide written notice to AIS at least 60 days prior to the end of the base period or the current option year, the term of SOW will then terminate at the end of the base period/current option year. Client may not terminate the SOW for convenience mid-year.

Monthly Fixed Priced Contracts

For projects where Client is being invoiced on a monthly Fixed Price basis and not a milestone basis. Client understands that the overall fee of the project is evenly distributed across the period of performance. Due to this, should the SOW be terminated early, Client understands that AIS may issue a close out invoice containing an adjustment fee to cover the difference between the fee of the scope of work completed prior to termination and the amount of fee which has been invoiced.

AIS Investment Funds

For projects where Client is receiving AIS investment funds, should client request to terminate the project early for convenience client will be required to reimburse AIS for any investment amount applied to services already provided to Client by AIS.

Msft Investment Funds (ECIFS)

For projects where Client is receiving funding by a third party for a portion of or all of the project, Client agrees that they are responsible for payment to AIS for any work already performed where AIS cannot receive payment from said third party due to early termination.

## Warranty

For Clients who have Warranty Provisions in their MSA which we wish to alter in the SOW please use this section to establish the Warranty Provisions for this SOW only.  If you are unsure, please reach out to Contracts to verify. If there is no need to alter the Warranty in the MSA this section can be removed.

# Validity of SOW

This can be a hard date or just number of days.

This statement of work is valid for 30 days from the date on the cover page. The client understands that if this agreement is not fully executed within 30 days that the availability of resources and prices may change.

# Closing

IN WITNESS WHEREOF, the Parties have caused this Statement of Work to be executed by their duly authorized representatives.

Agreed to:

| Customeridname |  | Applied Information Sciences, Inc. (AIS) |
| --- | --- | --- |
| By: |  | By: |
| Signature |  | Signature |
| Name (Type / Print) |  | Name (Type / Print) |
| Title (Type / Print) |  | Title (Type / Print) |
| Date |  | Date |

☒Check here if Client will initiate a PO for this SOW.

Client understands that if a PO will be initiated, they must provide a copy of PO and PO Number to AIS at the time this document is executed.